Working Group Minutes

STC Neighbourhood Plan

15th September 2020 at 10am

Location: Microsoft Teams

Attendance list: Cllr P Bedford, Cllr S Bolton, Cllr G Derx, Cllr H Fisher, Cllr B Segal, The Clerk Mrs K. Evans, Ellen Krier and Dale Turner – Pegasus, Dave Chapman – Locality

| Topic | Discussion | Action | Person Responsible |
| --- | --- | --- | --- |
| 1. Apologies for absence | None. |  |  |
| 2. Progress update | PB reported that very little progress had been made due to the Covid-19 outbreak. He explained that the Towns Deal fund could be a possible injection of up to £25million that would positively impact the community in Stainforth. He also stated that placing the pit gears as a monument in the middle of a country park is often known to fail and reported that Waystone are reluctant to build housing on the site as this would reduce housing prices and compromise the development of the marina. It was noted that DMBC are currently paying out circa £300k per annum to secure the pit site and that the condition survey undertaken by Bonsers found them structurally stable for at least the next 10 years. DC GD stated that the Townsdeal criteria includes leisure and education, therefore the museum and country park would be able to be a part of this. PB explained that the pit gears and the country park are the top priorities and that Unity should not be let off with the responsibility. Ellen & Dale stated that they were happy with the brief as initially discussed. The Town Council all agreed that they were happy to commission Pegasus. DC suggested that a cycle path is a possibility in order to connect the canal to the railway interchange through the country park / by the pit gears. He also suggested that it should have connection to the marina. It was discussed that Towns deal fund deadline was the 31st of March 2021. | Circulate Condition Survey to DC, EK & DT. PB and Mrs KE commission Pegasus and discuss finer details with Ellen and Dave | KE PB, Mrs KE |
| 3. Date of next meeting | To be arranged. |  |  |

Close of meeting 11.30am